OPTIMIZELY — CMS & DAM DEMO PROJECT PLAN

# Länsförsäkringar Demo Environment

Kick-off held — build sprint: Week 35–36  |  Owner: Md Tarek Rahman

# 1. Context

Länsförsäkringar (LF) is defining its target architecture for the next 5–10 years across CMS, CRM, CDP, CSM and DAM. LF selected other vendors for CRM/CDP but has shortlisted Optimizely (and likely one other vendor) for CMS and DAM. They currently run CMS 12 on-prem; the goal is to move them to SaaS CMS 13.

A dedicated demo tenant will be built by re-skinning the existing bank demo (bank.optimizely-demos.com) toward LF's brand, with a self-service sandbox LF stakeholders can explore after a series of workshops.

# 2. Timeline

| Week | Milestone |
| --- | --- |
| Wk 34 (this week) | Kick-off held. Tenant provisioning request raised. Repo forked. |
| Wk 35 | Product enablement complete (CMS 13, CMP, DAM, Forms, EXP, Opal, Graph). Branding tokens + IA applied. DAM populated. Multi-site skeleton (global + Stockholm + Skåne) live. |
| Wk 36 | Calculators built and wired to Graph. Forms, Translations, Personalization, Experimentation showcases complete. Integration wiring (CMS↔Graph↔DAM↔CMP↔EXP↔Forms↔Opal) finished. Customer invite + sandbox doc sent. |
| Wk 37+ | Workshops with LF stakeholders. LF self-service scenarios. Iterate on feedback. |

# 3. Workstream tracker

Repo-buildable work can proceed in this codebase now. Non-repo items require an internal Optimizely provisioning/ops request and are outside what can be done directly in the repository.

| # | Workstream | Repo / Non-repo | Blocked by |
| --- | --- | --- | --- |
| 1 | Tenant & provisioning | Non-repo (ops) | — |
| 2 | Customer access & sandbox onboarding | Non-repo (ops) | #1 |
| 3 | Repo & environment access | Repo/ops | — |
| 4 | Branding & visual alignment to LF | Repo | #3 |
| 5 | DAM showcase | Repo + tenant config | #1, #12 |
| 6 | Forms showcase | Repo + tenant config | #1, #12 |
| 7 | Translations showcase | Repo + tenant config | #1, #12 |
| 8 | Multi-site / global-local components | Repo + tenant config | #1, #12 |
| 9 | Personalization showcase | Repo + tenant config | #1, #12 |
| 10 | Experimentation showcase | Repo + tenant config | #1, #12 |
| 11 | Calculators (1-2) | Repo | #1, #3, #12 |
| 12 | Product integration & architecture wiring | Repo + tenant config | #1 (sequence early — blocks 5-11) |

## 4. Tenant & provisioning (non-repo)

- Raise request for a dedicated Opti ID tenant (e.g. lansforsakringar-demo).

- Enable and verify: SaaS CMS (v13), CMP, DAM, Forms, Experimentation (Web + Feature), Opal, Graph.

- Confirm data retention / teardown plan for the tenant after the evaluation.

## 5. Customer access (non-repo)

- Get the list of LF stakeholders to invite (ask William/David for names + roles).

- Test the invite flow end-to-end with an external email address before sending to LF.

- Confirm the SSO story: LF requires Entra/M365 SSO with Entra-group-based provisioning; be ready to explain this even if the demo tenant uses plain Opti ID logins.

- Write a one-page "getting started in the sandbox" doc (URLs, logins, what to try, who to contact).

## 6. Repo & environment access

- Get git access for yourself and anyone helping build.

- Fork/branch the bank demo repo rather than editing it in place.

- Confirm the CI/CD path from repo to demo environment, with no single-person bottleneck.

- Document the local dev setup so a second person can pick up work.

- Confirm who owns the environment during LF's self-service period.

## 7. Branding & visual alignment

Target: recognizably LF, not a pixel-perfect clone. Set expectations that this is directional.

- Pull LF brand basics from the live site: primary blue, accent colors, typography, logo treatment, button/card styling, corner radii, spacing rhythm.

- Apply as design tokens, not hard-coded CSS — LF's own roadmap is design tokens + Web Components + Lit, so tokenized theming speaks directly to it.

- Swap imagery for insurance/banking-appropriate assets, sourced through DAM so the DAM story is live.

- Replace copy with Swedish where visible in the main flows.

- Header, footer, navigation loosely matching LF's IA (Privat / Företag, regional selector).

- Check accessibility basics — contrast, focus states. LF is a regulated financial institution.

## 8. Feature showcases

DAM

- Populate a realistic asset library: images, logos, video, brand fonts, document templates.

- Show metadata, tagging and search.

- Show asset reuse across CMS pages, CMP campaigns and multi-site.

- Show rights/expiry or approval workflow if available.

- Position DAM as an independently consumable service with an API, not a CMS feature — LF's current DAM (Media Bank + Quick Channel) is what they want to consolidate away from.

- Bonus: show DAM serving design-system assets.

Forms

- Build 1–2 realistic forms (contact request, callback booking, claim start).

- Show conditional logic, validation, multi-step.

- Show submission handling and where data goes.

- Show a form embedded inside a headless/decoupled front end, not just a CMS page.

Translations

- Swedish as secondary, English primary, Danish as third.

- Show the editor translation workflow and fallback behavior.

- Test Opal translation.

Multi-site / global vs. local components

- Single most important structural demo — LF's 23 mutual companies want local control, the centre wants brand consistency.

- Set up a global site + at least 2 regional sites (e.g. Stockholm, Skåne).

- Show globally-governed components regions cannot alter, and locally-editable components/content.

- Show shared DAM assets and shared component library across sites.

- Show what a regional editor sees vs. a central editor (permissions in action).

Personalization

- Anonymous → known visitor journey.

- Regional personalization (mutual/association-based) — their current real-world use case.

- Offer/product personalization layered on top.

- Show the CMS-side vs. Experimentation-side personalization boundary.

- Be ready to talk latency: personalization within 200ms out of the box, edge delivery below that, feature flags evaluating in 2–5ms via SDK datafile.

Experimentation

- At least one live web experiment on the demo site.

- One feature experiment/flag to show the developer-side path.

- Show roles and permissions governing who can launch what.

- Have a point of view on canary releases.

## 9. Calculators (1–2)

Reference: lansforsakringar.se mortgage / lånelöfte guide.

- Suggested pair: mortgage/lånelöfte guide (high value, multi-step) + a simpler insurance premium estimator (shows the pattern is repeatable cheaply).

- Build as a standalone component/micro frontend, consumable by web and mobile hosts.

- Content, labels and legal copy sourced from CMS via Graph — proves content decoupling.

- Calculation logic lives in the front end or a small service, not the CMS.

- Demo an editor changing a label/disclaimer/interest assumption and it appearing without a redeploy — answers LF's #1 friction point (hard-coded content requiring code deploys).

- Instrument with an experiment or event so it feeds the analytics story.

- Keep the maths plausible but clearly marked as illustrative.

## 10. Product integration & architecture wiring

Flagged as the biggest lift — sequence it early; it blocks the feature demos.

- CMS ↔ Graph — content served headlessly to the front end (answers the channel-agnostic delivery question).

- CMS ↔ DAM — assets referenced from CMS, single source of truth.

- CMP ↔ CMS/DAM — campaign planning through to published content.

- CMS ↔ Experimentation — content variants and personalization.

- Forms ↔ CMS — and where submissions land.

- Opal — wired into at least one editorial workflow, not a bolt-on slide.

- Micro frontend proof point — at least one part of the site rendered as an independently deployed component consuming CMS content via Graph (LF is moving to per-bounded-context micro frontends with native iOS/Android hosts).

- Analytics — show or credibly mock the Databricks-native pattern; cohorts usable in both CMS and Experimentation is the differentiator vs. the CDP-connector route.

- Azure Front Door — have a clear, resolved answer on high-performance edge personalization behind AFD (Jim's open objection).

# 11. Open risks & talking points to prepare

- Databricks / Confluent cost sensitivity (Tobias) — governance story around cohorts staying in LF's own Databricks.

- Azure Front Door + edge personalization (Jim) — resolve properly rather than leaving the assumption standing.

- Canary releases positioning (Jim) — have a considered point of view ready.

- DAM as a swappable, independent component (Risto already set this expectation with LF).

- WCAG / accessibility gaps — LF is a regulated financial institution; keep this tight.